Full Title of Presentation
Presentation of Task and Project Plan
Drone Formation Control Simulator
Michael Faber,
Christian Grüneberg,
Sourav Salkoppalu Lingaraju,
Belvin Benny Thomas
Autonomous Multisensor Systems Group
Institute for Intelligent Cooperating Systems
Faculty of Computer Science
Otto von Guericke University Magdeburg
14.11.2024

---
Requirements for Powerpoint Template
Outline
- Project tasks
- Milestones
- Timeline
- Responsibilities

---
Hints
Project tasks
- ROS 2 Gazebo Simulation for Drone Formations
- Communications between agents
- Implementation of formation control
- Implementation of event based communications

---
Nice Topic
Milestones
- Drone control
- Communication
- Formation Control
- State estimation

---
 Timeline
- Infrastructure setup - 2 Weeks until 28. November
- Single drone simulated in Gazebo – 1 Month until 28. December
- Multiple Drones simulated without communication – 2 Weeks until 11. January
- Communication between Drones – 2 Weeks until 25. January
- Implementation of Formation – 2 Weeks until 7. February
- Estimation added and final optimization – 1 Month until 7. March
- Documentation and Report writing – until 31. March

---
 Responsibilities
- Programming – everyone
- Report - everyone
- Project management – Belvin
- Drone control – Sourav
- Communication – Michael
- Formation control – Christian
- State estimation - Belvin

---
Full Title of Presentation (2)
Presentation of Task and Project Plan
Drone Formation Control Simulator
Thank You For Your Attention!
Michael Faber,
Christian Grüneberg,
Sourav Salkoppalu Lingaraju,
Belvin Benny Thomas